## Sheet1
Gannt Chart |  |  | CC | Not Started | Completed | Completed Early | Completed Late
Week | [11 empty] | DUE ON 23/7
Phase I-Must | Timeline | Wk1 (12/5-18/5) | Wk2 (19/5-25/5) | Wk3 (26/5-1/6) | Wk4 (2/6-8/6) | Wk5 (9/6-15/6) | Wk6 (16/6-22/6) | Wk7 (23/6-29/6) | Wk8 (30/6-6/7) | Wk9 (7/7-13/7) | Wk10 (14/7-20/7) | Wk11 (21/7-23/7)
Login And Register | Projected
Actual
2 Factor Authentication | Projected
Actual
Create Blank Notes | Projected
Actual
View Notes | Projected
Actual
Edit Notes-Rich Text | Projected
Actual
Delete Notes | Projected
Actual
Sanitize All Inputs | Projected
Actual
Note Encryption | Projected
Actual
Local Saving | Projected
Actual
Works On Multiple Platforms | Projected
Actual
Comments
Phase II-Should
Create Notes Using A Template Or Format | Projected
Actual
Organisation Using Tags And Folders | Projected
Actual
Backup | Projected
Actual
Syncing Notes Across Devices | Projected
Actual
Comments
Phase III-Could
Sharing Notes | Projected
Actual
Exporting as PDF, txt | Projected
Actual
Self Destructing Notes | Projected
Actual
Comments
Phase IV-Documentation
DFD | Projected
Actual
Structure Chart | Projected
Actual
Class Diagram | Projected
Actual
Decision Tree | Projected
Actual